## Schedule
Programmer Name(s): | Evan Dent | James Latane
| Original | Original | Elapsed time at |  | Second | Second | Elapsed time after |  | Total | Total
| Estimate | Deadline | Intermediate Schedule |  | Estimate | Deadline | Intermediate Schedule |  | Time | Time
Task |  |  | Partner 1 | Partner 2 |  |  | Partner 1 | Partner 2 | Partner 1 | Partner 2
Buffer class | 1 | 2011-10-19 | 2 | 2 | 2 | 2011-10-26 |  | 0 | 2 | 2
File parser (SafeFile) | 1.5 | 2011-10-19 | 1 | 1 | 1.5 | 2011-10-27 |  | 0 | 1 | 1
Buffer pool | 2.5 | 2011-10-21 | 2 | 2 | 3 | 2011-10-27 | 1 | 1 | 3 | 3
Stats | 1 | 2011-10-16 |  | 0 | 1 | 2011-10-28 | 1 | 1 | 1 | 1
Execution time | 0.5 | 2011-10-26 |  | 0 | 0.5 | 2011-10-28 | 0.5 | 0.5 | 0.5 | 0.5
Build heap | 1 | 2011-10-14 | 1.5 | 1.5 | 2 | 2011-10-31 | 1.5 | 1.5 | 3 | 3
Heap sort | 1 | 2011-10-14 | 2.5 | 2.5 | 2.5 | 2011-10-31 | 0.5 | 0.5 | 3 | 3
Setup, spec reading, scheduling | 1.5 | 2011-11-01 | 3.5 | 3.5 | 4 | 2011-11-01 |  | 0 | 3.5 | 3.5
Command line parser | 0.5 | 2011-10-14 | 0.5 | 0.5 | 0.5 | 2011-11-01 |  | 0 | 0.5 | 0.5
Debugging | 3 | 2011-10-31 |  | 0 | 2 | 2011-11-01 | 8.5 | 8.5 | 8.5 | 8.5
Documentation | 1.5 | 2011-11-01 |  | 0 | 1 | 2011-11-01 | 1 | 1 | 1 | 1
|  |  |  | 0 |  |  |  | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0
Sum of tasks | 15 | 2011-11-01 | 13 | 13 | 20 | 2011-11-01 | 14 | 14 | 27 | 27
Notes:
* All estimates should be to the nearest hour or half hour.
* If you work with a partner, there is an elapsed time column for each. If you do not work with a partner, delete the second column.
* Elapsed times should be in hours, can be measured to the half hour.
* “Original Estimate” is how many hours you originally think the task will take.
* “Original Deadline” is the date that you plan to complete this task. Not all tasks should have the same deadline!
* “Elapsed time at Intermediate Schedule” is how many hours you (and your partner) have spent when the intermediate schedule is turned in.
* “Second Estimate” is how many (total) hours you estimate the task will take at the time when you submit the intermediate schedule.
* “Second Deadline” is your revised deadline for completing the task. If the task is already completed at this point, say so.
* “Total time” is the total number of hours spent on the task when you turn the project in. If you work with a partner, show this time for both.
* “Sum of tasks” row should contain sums for the columns. Make sure that you compute this correctly for each column.
* You should add to the list of tasks in this template.
Formulas:
Second = [James Latane]
Second = MAX(G7:[Second, row above])